## Start Here
Project Tracker
Tasks · timeline · milestones · daily check-ins · learning · risks, all in one workbook.
Go to
▸ Dashboard | Live overview: KPIs, project health, member focus picker, deadlines and charts.
▸ Tasks | Your to-do list. One row per task with owner, status, priority, dates and progress.
▸ Timeline | Gantt chart built automatically from the Tasks sheet. Change the start date to scroll.
▸ Milestones | Big checkpoints. % done is calculated from the tasks linked to each one.
▸ Check-ins | Daily stand-up log: what I did, what's next, what's blocking me, and my mood.
▸ Learning | Skills matrix: every member tracks the topics they're learning.
▸ Risks & Issues | What could go wrong, how bad it is (score), who owns it, and the plan.
▸ Settings | Project name, dates, time zone, team members and drop-down lists.
Set up in 3 steps
1 · Settings: type your project name, start and end dates, time zone and team members.
2 · Milestones: list your big checkpoints. Then add tasks on the Tasks sheet and link each one to a milestone.
3 · Every day: update task status and progress, and add a short row on Check-ins. The Dashboard does the rest.
Colour key
Blue text | Cells you type in (inputs).
Grey cells | Calculated by formulas: don't type here.
Purple italics | Example rows: overwrite or delete them.
Red | Overdue, blocked or high risk: needs attention.
Tips
• Use the filter arrows on each header row to see only your own tasks, or only open ones.
• Share the workbook through OneDrive, SharePoint or Google Drive so everyone edits the same copy.
• The Dashboard is protected so its formulas can't be broken by accident (Review → Unprotect Sheet, no password).
• All dates and times are shown in the time zone set on the Settings sheet (currently: Local time), 12-hour AM/PM.
• Need more rows? Tasks has 300, Check-ins 500, Learning 150 and Risks 100 ready to use.

## Dashboard
Tasks |  |  | Done |  |  | % complete |  |  | Avg. progress |  |  | Days to deadline
Overdue |  |  | Due in 7 days |  |  | Blocked |  |  | Unassigned (open) |  |  | High risks open
Project health
Time elapsed | [8 empty] | Rule: at risk if anything is overdue or blocked; behind if work done trails time elapsed by more than 15 points.
Work complete
Member focus | [5 empty] | Next deadlines (open tasks)
Pick a member ▸ | Alex (example) |  |  |  |  | Due | Task |  |  | Owner | Status
Open tasks
Done
Overdue
Open hours (est.)
Next due
Next task
Last check-in
Learning done
Tasks by status |  |  | Open tasks by priority
Status | Tasks |  | Priority | Open
Team workload & engagement | [7 empty] | Weekly progress (burn-up)
Member | Open | Done | Overdue | Hours open | Check-ins (7d) | Learning % |  |  | Week of | Completed | Cumulative | Total tasks
#N/A hides future weeks in the chart.

## Settings
Settings
Set up your project here first. Everything else reads from this sheet.
← Back to Start Here
Project details |  |  |  | Drop-down lists (edit to customise)
Project name | My Project |  |  | Task status | Priority | Progress | Learning | Risk status | Mood
Project lead | Your name |  |  | Not started | Critical | 0% | Not started | Open | Great
Start date | 2026-10-09 |  |  | In progress | High | 25% | In progress | Monitoring | Good
End date / final deadline | 2026-12-04 17:00 |  |  | In review | Medium | 50% | Done | Closed | OK
Time zone shown in dates | Local time |  |  | Blocked | Low | 75% |  |  | Struggling
Description | One or two sentences on what this project delivers and for whom. |  |  | Done |  | 100%
Team members
Name | Role | Email / contact | GitHub / handle
Alex (example) | Lead
Sam (example) | Member
Jordan (example) | Member |  |  | Note: task status 'Done' and 'Blocked' are used by formulas: rename them only together with the formulas.

## Tasks
Tasks
One row per task. Type in the blue cells; grey columns are calculated. Dates: Local time, 12-hour AM/PM.
← Back to Start Here
ID | Task | Milestone | Owner | Status | Priority | Start | Due | Completed on | Est. hours | Progress | Days left | Health | Depends on | Notes / link | sort key
| Example: write the project brief | Planning | Alex (example) | Done | High | 2026-10-09 | 2026-10-12 17:00 | 2026-10-09 | 3 | 100% |  |  |  | Example row: overwrite or delete
| Example: set up the shared workspace | Planning | Sam (example) | In progress | Medium | 2026-10-09 | 2026-10-15 12:00 |  | 2 | 50% |  |  |  | Example row
| Example: build the first version | Build | Jordan (example) | Not started | Critical | 2026-10-16 | 2026-11-08 17:00 |  | 20 | 0% |  |  | T-002 | Example row
Note on A5: Filled in automatically when you type a task name.
Note on B5: What needs to be done, in a few words. Start with a verb: 'Write…', 'Fix…', 'Review…'.
Note on C5: Which milestone (phase) this task belongs to. List them on the Milestones sheet.
Note on D5: Who is doing it. Names come from Settings → Team members. Leave empty if nobody has picked it up yet.
Note on E5: Not started → In progress → In review → Done. Use Blocked when you're stuck.
Note on F5: Critical = the project fails without it. High = important. Medium / Low = nice to have.
Note on G5: When work starts. Used to draw the bar on the Timeline.
Note on H5: Deadline (date and time). Overdue tasks turn red.
Note on I5: The date you finished. Feeds the weekly progress chart.
Note on J5: Rough guess of the hours needed. Used to balance the workload.
Note on K5: How far along it is: 0%, 25%, 50%, 75% or 100%.
Note on L5: Calculated: days until the due date.
Note on M5: Calculated: On track / Due soon (3 days or less) / Overdue / Blocked / Done.
Note on N5: ID of a task that must finish first, e.g. T-002.
Note on O5: Anything useful: links, files, decisions.

## Milestones
Milestones
Big checkpoints or phases. Tasks are linked to a milestone with the Milestone column on the Tasks sheet.
← Back to Start Here
# | Milestone | Target date | Owner | Tasks | Done | % done | Status | Notes
| Planning | 2026-10-16 17:00 | [5 empty] | Example milestone
| Build | 2026-11-13 17:00 | [5 empty] | Example milestone
| Launch | 2026-12-04 17:00 | [5 empty] | Example milestone

## Timeline
Timeline (Gantt)
Read-only view of the first tasks on the Tasks sheet. Bars run from Start to Due. The gold column is today.
← Back to Start Here |  |  |  | Show from: |  | ← change this date to scroll the timeline
Legend: | Planned | Done | Overdue | Blocked | Today
Task | Owner | Status | Start | Due

## Check-ins
Daily Check-ins
Team progress: one short row per person per day. Anything typed in 'Blocked by' turns red so the lead sees it.
← Back to Start Here
Date | Member | What I did | What I'll do next | Blocked by | Hours | Mood | Task ID
2026-10-09 | Alex (example) | Wrote the project brief and shared it | Review feedback with the team | — | 2 | Good | T-001
Note on A5: Today's date (Ctrl + ; types it for you).
Note on B5: Your name (drop-down).
Note on C5: What you finished since your last check-in.
Note on D5: What you'll work on next.
Note on E5: Anything stopping you. Write '—' if nothing. Text here turns red so the lead notices.
Note on F5: Hours you spent (optional).
Note on G5: How you feel about your work (optional).
Note on H5: Related task ID from the Tasks sheet, e.g. T-004 (optional).
Note on A6: Example row (purple italics): overwrite it with your first real check-in.

## Learning
Learning Progress
Skills the project needs. Each member marks their own column: Not started → In progress → Done.
← Back to Start Here
# | Area | Topic | Resource (click) | Est. hours | Team done | Team %
Topics done →
% of topics done →
Study hours done →
| Example area | Example topic | Example resource (link) | 2 |  |  | Not started | Not started | Not started
Note on C5: What to learn.
Note on D5: Click to open the free resource.
Note on E5: Rough study time.
Note on F5: Calculated: how many members finished this topic.
Note on H5: Each member has a column: pick Not started / In progress / Done for each topic.

## Risks & Issues
Risks & Issues
Anything that could go wrong (risk) or already has (issue). Score = likelihood × impact (1–5 each).
← Back to Start Here
ID | Risk or issue | Type | Likelihood (1-5) | Impact (1-5) | Score | Level | Owner | Mitigation / next step | Status | Review by
| Example: key person unavailable near the deadline | Risk | 2 | 4 |  |  | Alex (example) | Pair up on every critical task | Open
Note on B5: Describe what could go wrong (risk) or what already went wrong (issue).
Note on D5: How likely is it? 1 = very unlikely … 5 = almost certain.
Note on E5: How bad would it be? 1 = minor … 5 = project fails.
Note on F5: Calculated: likelihood × impact. 15+ is High, 8–14 Medium.
Note on I5: What you'll do to prevent it or limit the damage.
Note on J5: Open → Monitoring → Closed.