## Dashboard
LineShine · AKT26 Hackathon Dashboard
Team ID 1065 · Everything here is calculated from the other sheets: don't type on this page.
Today (Cairo): |  | Next deadline:
Key numbers
Total tasks |  | Done |  | % complete
In progress / review |  | Blocked |  | Overdue
Points secured |  | Unassigned open tasks |  | Team learning done
Progress by assignment
Assignment | Tasks | Done | % done | Points done | Points total | Overdue
Team overview
Member | Open tasks | Done tasks | Check-ins | Last check-in | Learning done | Study hours
How to use this workbook
1. Tasks: add one row per task. Pick the assignment, assignee, status and priority from the drop-downs. Days left and Overdue fill in by themselves.
2. Daily Check-ins: each person adds one short row per day (what I did, what's next, what blocks me).
3. Learning: each person sets their own column to Not started / In progress / Done for every topic.
4. Team: add GitHub usernames and contacts. Lists: add new statuses or assignments (e.g. Week 2).
Colour key: blue text = cells you type in · grey cells = calculated, don't edit · red = overdue or blocked.
All dates and times are Cairo time, shown in 12-hour AM/PM format.

## Tasks
Task Tracker
One row per task. Fill the blue cells; grey columns are calculated. All times are Cairo time (12-hour AM/PM).
ID | Task | Assignment | Category | Assignee | Status | Priority | Points | Start date | Due (Cairo time) | Completed on | Days left | Overdue? | Notes / link
| Rename notebook, set TEAM_ID = 1065 and TEAM_NAME | Setup | Setup |  | Done | High |  | 2026-10-03 | 2026-10-10 14:59 | 2026-10-09
| Task 1 – Data-quality audit and issue log | Week 1 | Notebook |  | Done | High | 15 | 2026-10-03 | 2026-10-10 14:59 | 2026-10-09
| Task 2 – Consistency, validity and timeliness fixes | Week 1 | Notebook |  | Done | High | 15 | 2026-10-03 | 2026-10-10 14:59 | 2026-10-09
| Task 3 – Imputation study | Week 1 | Notebook |  | Done | High | 15 | 2026-10-03 | 2026-10-10 14:59 | 2026-10-09
| Task 4 – Outliers and transformations | Week 1 | Notebook |  | Done | Medium | 10 | 2026-10-03 | 2026-10-10 14:59 | 2026-10-09
| Task 5 – Leak-free pipeline + TimeSeriesSplit CV | Week 1 | Notebook |  | Done | High | 15 | 2026-10-03 | 2026-10-10 14:59 | 2026-10-09
| Task 6 – Impact study on the test year | Week 1 | Notebook |  | Done | High | 20 | 2026-10-03 | 2026-10-10 14:59 | 2026-10-09
| Final summary cell | Week 1 | Notebook |  | Done | High | 10 | 2026-10-03 | 2026-10-10 14:59 | 2026-10-09
| Bonus – parallel per-station cleaning (HPC) | Week 1 | Bonus |  | Done | Medium | 10 | 2026-10-03 | 2026-10-10 14:59 | 2026-10-09
| Team review of the notebook + Restart & Run All | Week 1 | Review |  | Not started | High |  | 2026-10-03 | 2026-10-10 14:59
| Upload notebook via the Google Form (team leader) | Week 1 | Submission |  | Not started | High |  | 2026-10-03 | 2026-10-10 14:59
| Keep beijing_clean_team1065.csv.gz for Week 2 | Week 1 | Data |  | Done | Medium |  | 2026-10-03 | 2026-10-10 14:59 | 2026-10-09
Note on J5: Organiser deadline: Oct 9 2026, 11:59 PM Anywhere-on-Earth = Sat Oct 10 2026, 2:59 PM Cairo (EEST, UTC+3).

## Daily Check-ins
Daily Check-ins (team progress)
One row per person per day. Keep it short. The grey example row shows the format; delete it once you add real rows.
Date | Member | What I did | What I'll do next | Blocked by | Hours | Related task ID
2026-10-09 | Anas Elgalad | Ran the full notebook; checked every answer cell against the outputs | Review the final summary with the team | — | 2.5 | T-010
Note on A5: Example row: replace or delete it.

## Learning
Learning Progress
Each member marks their own status per topic (Not started / In progress / Done). Topics come from docs/learning-resources.md.
# | Area | Topic | Resource | Est. hours | Team done | Team % done | Abdallah Ismail | Omar Seifelnasr | Abdulrahman Omran | Anas Elgalad | Mohamed Abd Elaal | Mohamed Salah
Per-member progress →
Share of topics done →
Hours of study done →
1 | Python data wrangling | pandas basics | Kaggle Learn: Pandas | 4 |  |  | Not started | Not started | Not started | Not started | Not started | Not started
2 | Python data wrangling | groupby, pivot, time series | pandas User Guide |  |  |  | Not started | Not started | Not started | Not started | Not started | Not started
3 | Python data wrangling | NumPy, pandas, matplotlib | Python Data Science Handbook |  |  |  | Not started | Not started | Not started | Not started | Not started | Not started
4 | Data quality and cleaning (Tasks 1–2) | Missing values, scaling, dates, encodings | Kaggle Learn: Data Cleaning | 4 |  |  | Not started | Not started | Not started | Not started | Not started | Not started
5 | Data quality and cleaning (Tasks 1–2) | Missing data in pandas | pandas: Working with missing data | 0.5 |  |  | Not started | Not started | Not started | Not started | Not started | Not started
6 | Data quality and cleaning (Tasks 1–2) | The dataset | UCI 501: Beijing Multi-Site Air Quality | 0.25 |  |  | Not started | Not started | Not started | Not started | Not started | Not started
7 | Imputation (Task 3) | Simple/KNN/Iterative imputers, missing indicators | scikit-learn: Imputation | 0.75 |  |  | Not started | Not started | Not started | Not started | Not started | Not started
8 | Imputation (Task 3) | Limited time interpolation | pandas `Series.interpolate` | 0.25 |  |  | Not started | Not started | Not started | Not started | Not started | Not started
9 | Imputation (Task 3) | MCAR / MAR / MNAR | Flexible Imputation of Missing Data, ch. 1–2 | 1 |  |  | Not started | Not started | Not started | Not started | Not started | Not started
10 | Outliers and transformations (Task 4) | Log, power and quantile transforms | scikit-learn: Preprocessing | 0.5 |  |  | Not started | Not started | Not started | Not started | Not started | Not started
11 | Outliers and transformations (Task 4) | Outlier detection | scikit-learn: Novelty and outlier detection | 0.5 |  |  | Not started | Not started | Not started | Not started | Not started | Not started
12 | Outliers and transformations (Task 4) | Outlier basics | NIST e-Handbook: Detection of outliers | 0.33 |  |  | Not started | Not started | Not started | Not started | Not started | Not started
13 | Leak-free pipelines and time-series CV (Tasks 5–6) | Pipeline, ColumnTransformer, TransformedTargetRegressor | scikit-learn: Composite estimators | 0.75 |  |  | Not started | Not started | Not started | Not started | Not started | Not started
14 | Leak-free pipelines and time-series CV (Tasks 5–6) | **Data leakage** | scikit-learn: Common pitfalls | 0.75 |  |  | Not started | Not started | Not started | Not started | Not started | Not started
15 | Leak-free pipelines and time-series CV (Tasks 5–6) | TimeSeriesSplit | scikit-learn: Time series CV | 0.33 |  |  | Not started | Not started | Not started | Not started | Not started | Not started
16 | Leak-free pipelines and time-series CV (Tasks 5–6) | HistGradientBoosting | scikit-learn: Gradient boosting | 0.5 |  |  | Not started | Not started | Not started | Not started | Not started | Not started
17 | Leak-free pipelines and time-series CV (Tasks 5–6) | Pipelines, CV, leakage (course) | Kaggle Learn: Intermediate ML | 4 |  |  | Not started | Not started | Not started | Not started | Not started | Not started
18 | Leak-free pipelines and time-series CV (Tasks 5–6) | RMSE / MAE / R² | scikit-learn: Regression metrics | 0.33 |  |  | Not started | Not started | Not started | Not started | Not started | Not started
19 | Leak-free pipelines and time-series CV (Tasks 5–6) | Time-series thinking | Forecasting: Principles and Practice (3rd ed.) |  |  |  | Not started | Not started | Not started | Not started | Not started | Not started
20 | HPC / parallel computing (bonus) | joblib Parallel | joblib: Embarrassingly parallel for loops | 0.5 |  |  | Not started | Not started | Not started | Not started | Not started | Not started
21 | HPC / parallel computing (bonus) | Dask | Dask Tutorial | 2 |  |  | Not started | Not started | Not started | Not started | Not started | Not started
22 | HPC / parallel computing (bonus) | Speed-up, efficiency, Amdahl's law | Wikipedia: Amdahl's law | 0.33 |  |  | Not started | Not started | Not started | Not started | Not started | Not started
23 | Teamwork tooling | Git | Pro Git book, ch. 1–3 | 2 |  |  | Not started | Not started | Not started | Not started | Not started | Not started
24 | Teamwork tooling | GitHub Projects | GitHub Docs: About Projects | 0.33 |  |  | Not started | Not started | Not started | Not started | Not started | Not started
25 | Teamwork tooling | Notebook diff and merge | nbdime | 0.25 |  |  | Not started | Not started | Not started | Not started | Not started | Not started
26 | Teamwork tooling | Scrum | Atlassian: Scrum | 0.25 |  |  | Not started | Not started | Not started | Not started | Not started | Not started
Note on E9: Rough study time from docs/learning-resources.md ('ref' items have no estimate).

## Lists
Lists
Drop-down values used across the workbook. Edit here to add statuses or assignments.
Task status | Priority | Learning status | Assignment
Not started | High | Not started | Week 1
In progress | Medium | In progress | Week 2
In review | Low | Done | Week 3
Blocked |  |  | Week 4
Done |  |  | Week 5
Setup

## Team
Team LineShine · Team ID 1065
Member list feeds the drop-downs. Add GitHub usernames and contact details in the blue cells.
Member | Role | GitHub username | Email / phone | Tasks open | Tasks done | Check-ins logged | Learning done %
Abdallah Ismail | Team leader
Omar Seifelnasr | Member
Abdulrahman Omran | Member
Anas Elgalad | Member
Mohamed Abd Elaal | Member
Mohamed Salah | Member